## Slide 1
APRM senisitisation project in Namibia (ASPIN) working group meeting
25 July 2018
Steven Gruzd

## Slide 2
10h00 – 10h10 | Welcome and Introduction to APRM Mr Steven Gruzd, Programme Head, African Governance and Diplomacy. SAIIA
10h10 – 10h20 | Update on Namibian APRM Process Mr Graham Hopwood, Executive Director, IPPR.
10h20 – 10h35 | Recap on Civil Society Training Workshop in April Ms Cayley Clifford, Research Scholar, African Governance and Diplomacy. SAIIA Initial issues identified
10h45 – 11h15 | Session One: Working Group Facilitated by Graham Hopwood Participants How the group should operate Division of responsibilities Timetable
11h15 – 12h30 | Session Two: Governance Issues Facilitated by Steven Gruzd Identification of 12 major governance issues in Namibia, how to marshal evidence and prepare the submission
12h30 – 13h00 | Consolidation and Closing Presentation of submission format Scheduling of submission writing visit and other milestones

## Slide 3: ASPIN: A brief recap
Working with Namibian CSOs to make a written submission to the national APRM process by November 2018
Partnership between SAIIA and IPPR
Support from OSISA and FES

## Slide 4: TIMELINE
19-20 January – scoping visit, SAIIA in Namibia
25-27 January – donor meeting, IPPR in SA
17-18 March - 2 day training workshop, met National Assembly, established working group
25 July – working group meeting, decide 12 issues
August/September – submission writing visit
October/November – circulate draft, validation workshop visit, develop advocacy plan